## Slide 1: Ascension Health: A System Model of Pressure Ulcer Success and Spread
July 2012

## Slide 2: Case Exemplars Pressure Ulcers
Results
Ascension Health nursing
developed, tested and
implemented an evidence-based
program to eliminate pressure ulcers
Achieved a 94% reduction from
the national average rate
$60M investment from CEOs for
bed frames and surfaces
Less than 1 per 1,000 patient days

## Slide 3: Taking Action
Ascension Health committed itself to the elimination of hospital-acquired pressure ulcers
Our initiative started in 2003
We took a comprehensive approach
We established a system-wide standard of care

## Slide 4: How did change occur this quickly? Practice ► Process ► Product
Early Adopter Ministries
  Results & recommendations were adopted and spread for system-wide change
Chief Nursing Officer Leadership
  Business case aligned product
  Nursing convened key partners (Finance, Supply Chain, Physicians, C-suite, Allied Health, Risk, Legal)
Product was expedited for the bed and surface replacement plan
Outcomes and Transparency
  Change practice
  Validate behaviors

## Slide 5: Pressure Ulcer Implementation Timeline
2004
2005
2006
February 2004
PFA Initial Meeting
June 2004
Expert Meeting Alpha
August 2004
Bundle Implementation Alpha
November 2004
Surfaces Replaced Alpha
March 2005
Prevalence Study
June 2005
Pressure Ulcer Summit
November 2005
Toolkit Implementation
January 2006
Bundle Implementation System
March 2006
Ascension Health Prevalence Study
June 2006
Ascension Health Standardized Care
and Measurement

## Slide 6: Pressure Ulcer Elimination “Bundle” = SKIN
Tissue injury can be more than skin deep…
S
K
I
N
Manage Nutrition and Hydration
Manage Incontinence
Keep Patients Moving
Selection of Appropriate Support Surfaces

## Slide 7: Surface Selection
    Assess patient needs and use evidenced-based criteria for surface selection
    Use pressure reduction surfaces on beds and chairs
    Keep heels elevated off surfaces
    Utilize pressure reduction surfaces and devices during operative procedures
S
K
I
N
NOTE: Pressure reduction/relief devices are adjuncts and not replacements for repositioning

## Slide 8: Keep Patients Moving
    Ensure turning and prevent prolonged
    sitting for all at-risk patients regardless
    of ability to move self
    Schedule regular and frequent turning and
    repositioning for patients who are bed- and chair-bound
    Turn patients at least every 2 hours
    Avoid continuous sitting
    Instruct patient to shift weight every 15 minutes
    if able, if not reposition patient in chair every hour
S
K
I
N

## Slide 9: Incontinence Management
Consider the etiology of urinary and fecal incontinence
Gently clean and dry the skin after every incontinent episode
Avoid hot water and use a mild cleansing agent to minimize irritation and drying of the skin
Minimize force and friction applied to skin
Use protective skin barriers to protect and maintain skin integrity
Utilize under pads that are absorbent and wick moisture away from the skin
Limit use of containment garments except for uncontained liquid stool, incontinent ambulatory patients, and patient request
Consider use of indwelling catheter for short period of time when incontinence has contributed to or may contaminate pressure ulcer
Consider fecal collection device to contain stool and protect skin
NOTE: Use of Foley catheters is contraindicated for use as fecal collection device
S
K
I
N

## Slide 10: Nutrition
Ensure that patients are fed and hydrated
Consult Registered Dietitian based on nursing assessment of nutritional risk
Implement a nutritional support and/or supplementation program for nutritionally compromised individuals
Monitor laboratory parameters for nutrition status
  Pre-albumin
  Albumin
  Total lymphocyte count
Manage blood glucose for optimum control
S
K
I
N